## Sheet1
WBS FYP AIR CANVAS
TASK | DAYS(EDA)
NOVEMBER
Project research | 5 days
Research about Eminist dataset | 3 days
Exploring Eminist dataset | 2 days
Reseach about opencv and media pipe | 3 days
DECEMBER
Learning Opencv basics | 6 days
Research on POC on handtracking | 2 days
Hand detection and finger tracking using contor detection via Opencv | 7 days
Version compatability issue between python and Opencv.
Identifying and resolving the issue | 4 days
Research of POC related to contor detection | 3 days
Mid terms break | 7 days
Inconsistency issue in finger tracking
JANUARY
Identifying the issue | 3-4 days
Trying different implementations for finger tracking | 5-6 days
Implementation of module for digit recognition | 3 days
Going for alternative solution for handtracking using media pipe | 3 days
Finger tracking using media pipe | 3-4 days
FEBRUARY
Trello and git setup | 2 days
Reasearch and POC on OCR and Capture air writing and convert it into image | 6 days
Capturing picture and convert it into image | 4-5 days
Implementation of OCR | 4-5 days
Error detection and correction | 3 days
MARCH
Integration of all the modules developed till now | 7-10 days
Testing | 2 days
Correction of any error/discrepancy etc | 3-4 days
Working on accuracy | 3 days
MID YEAR EVALUATION(Date not known) | 4-5 days
APRIL
Working on accuracy | 3 days
Research and development of text to speech recognition | 3 days